## Project Timeline
Project 4 Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
Date | Milestone | Assigned To | Position | Meeting Minutes | Deliverables
2020-12-14 | Project Start | Yong Tat, Jeffery, Yuanfeng, Katherine | 20 | Discussion of project approach | Work assignment among team members
2020-12-21 | Data Cleaning | Yuanfeng, Katherine | -20 | Discussion of findings from data cleanning | Finalize data cleaning strategy
2020-12-21 | EDA | Yong Tat, Jeffery | 20 | Discussion of observations from features in dataset given | Finalize the set of features to be used in project analysis
2020-12-28 | Modeling | Yong Tat, Yuanfeng | -20 | Discussion of model performance | Finalize best model and fine tune parameters
2020-12-28 | Cost Benefit Analysis | Jeffery, Katherine | 25 | Discussion of spraying strategy | Produce spray map and cost analysis
2021-01-04 | Finalization and Documentation | Yong Tat, Jeffery, Yuanfeng, Katherine | -20 | Prepare documents to be submitted | Finalize documents to be submitted
2021-01-08 | Presentation | Yong Tat, Jeffery, Yuanfeng, Katherine | 15 | Prepare presentation slides | Presentation slides